## Overview
FSCORD — Stage A Engineering Backlog
Foundation / code modernization (phases A0–A5, through the expansion-ready exit gate)
Scope | Stage A only. Stage B (art, audio, AI, modes, procedural, story, live-ops) begins after A5-10 passes.
How to use | Import the CSV into your tracker, or work the Backlog tab directly. One row = one task.
Estimate key | S = small, M = medium, L = large (relative sizing, not hours).
Priority key | Critical > High > Medium. Criticals are security/gate items — do them first.
Dependencies | 'Depends On' lists task IDs that should complete first.
Exit gate | A5-10 is the go/no-go for any Stage B creative spend.
Tasks per phase
A0 Safety, provenance & setup | 7
A1 Bootstrap & CI | 6
A2 Core framework | 9
A3 Gameplay parity on data | 12
A4 Pipelines & persistence | 7
A5 Backend, optimization & hardening | 10
TOTAL | 51

## Backlog
Epic / Phase | ID | Task | Description | Priority | Estimate | Depends On | Acceptance criteria | Status
A0 Safety, provenance & setup | A0-1 | Rotate AWS key pair | Revoke the committed ShmuelShmuel.pem key pair in AWS IAM/EC2 and generate a replacement stored in a secret manager. | Critical | S | - | Old key rejected on auth attempt; new key works; rotation logged. | To Do
A0 Safety, provenance & setup | A0-2 | Change exposed password & audit account | Change the password from Password.docx and review AWS account activity for unauthorized use. | Critical | S | - | Password changed; CloudTrail/billing reviewed; no unexpected activity, or incident raised. | To Do
A0 Safety, provenance & setup | A0-3 | Purge secrets from project & history | Remove AWS/ from the project and scrub the key + password from any version-control history. | High | S | A0-1,A0-2 | No secret present in working tree or git history (verified by scan). | To Do
A0 Safety, provenance & setup | A0-4 | Archive the 2015 project | Store an immutable, dated copy of the original Unity project and both APKs in cold storage. | High | S | - | Read-only archive exists and is restorable; checksum recorded. | To Do
A0 Safety, provenance & setup | A0-5 | Create Git repo + Git LFS | Initialize repo with a Unity 6 .gitignore and LFS patterns for models, textures, audio, and video. | High | S | - | Fresh clone builds; large binaries tracked by LFS; no engine temp files committed. | To Do
A0 Safety, provenance & setup | A0-6 | Decide studio name & bundle ID | Choose the studio/company name and final reverse-DNS bundle identifier (com.<studio>.fscord). | Medium | S | - | Bundle ID agreed and recorded; reserved on both stores if possible. | To Do
A0 Safety, provenance & setup | A0-7 | Install & pin Unity 6 LTS | Install Unity 6 LTS via Hub and pin one exact patch version for the whole team. | High | S | - | Agreed version documented in README; all machines on the same patch. | To Do
A1 Bootstrap & CI | A1-1 | Create Unity 6 URP mobile project | New URP (mobile) project using the target folder structure from the roadmap (4.4). | High | M | A0-7 | Project opens on the pinned version; folder structure in place; URP mobile renderer active. | To Do
A1 Bootstrap & CI | A1-2 | Add package stack | Add Input System, AI Navigation, Behavior, Addressables, UGS, LevelPlay, and Unity IAP. | High | S | A1-1 | Packages resolve and compile; versions pinned in manifest. | To Do
A1 Bootstrap & CI | A1-3 | Configure player settings | Set bundle ID, orientation, min SDK (Android) / iOS target, IL2CPP + ARM64, icons/splash placeholders. | High | S | A1-1,A0-6 | Android + iOS player settings correct; 64-bit only; builds locally. | To Do
A1 Bootstrap & CI | A1-4 | Set up signing in secret store | Create Android keystore and iOS provisioning; store credentials in CI secrets, never in repo. | High | S | A1-3 | Signed local build succeeds; no signing secret in source control. | To Do
A1 Bootstrap & CI | A1-5 | CI build pipeline | Pipeline builds signed Android + iOS artifacts from a commit (Unity Build Automation or GitHub Actions + Fastlane). | High | M | A1-4 | Green CI run produces installable signed artifacts for both platforms. | To Do
A1 Bootstrap & CI | A1-6 | Device smoke test | Install the empty URP build on a physical Android and iOS device. | Medium | S | A1-5 | App launches and renders on both devices; cold-start recorded as baseline. | To Do
A2 Core framework | A2-1 | Boot scene + service locator/DI | Boot scene that initializes services in order and hands typed references to systems. | High | M | A1-1 | Services initialize once at boot; no static-singleton sprawl; init order deterministic. | To Do
A2 Core framework | A2-2 | Event bus / signals | Typed publish/subscribe system for gameplay events (e.g. TankDestroyed). | High | M | A2-1 | Systems communicate via events; no GameObject.Find in new code; unit-tested. | To Do
A2 Core framework | A2-3 | Object pooling system | Generic pool for transient objects (shells, VFX, tanks, mines, floating text). | High | M | A2-1 | Pooled spawn/return with no per-use allocation; capacity configurable; tested. | To Do
A2 Core framework | A2-4 | Match Definition schema | Mode-agnostic ScriptableObject describing a match (spawns, waves, control points, objectives, win/lose). | High | M | A2-1 | A match can be fully described as data; schema documented for designers. | To Do
A2 Core framework | A2-5 | Match engine skeleton | Runtime engine that plays any Match Definition and emits state events. | High | L | A2-4,A2-2 | Engine drives a match end-to-end from data; emits start/wave/win/lose events. | To Do
A2 Core framework | A2-6 | Match-flow FSM | State machine: Intro -> Playing -> WaveBreak -> Victory/Defeat. | High | M | A2-5 | Match flow driven by the FSM; no boolean-flag state; transitions unit-tested. | To Do
A2 Core framework | A2-7 | Gesture input layer | Input System + Enhanced Touch: tap, circle, swipe, X, drag, shake, pan/rotate/pinch -> intent events. | High | L | A2-2 | All six weapon gestures + camera controls produce correct intent events; decoupled from effects. | To Do
A2 Core framework | A2-8 | Addressable scene loading | Additive scene load/unload via Addressables; retire Application.LoadLevel. | High | M | A1-2 | Scenes load additively via Addressables; no deprecated load calls remain. | To Do
A2 Core framework | A2-9 | Grey-box vertical test | Test scene wiring gestures -> pooled placeholder effects on the match engine. | Medium | M | A2-3,A2-7,A2-6 | All gestures fire pooled effects; a data-defined match runs start to finish. | To Do
A3 Gameplay parity on data | A3-1 | Weapon ScriptableObjects | Author HE, concentrated strike, napalm, daisy cutter, mines, nuke as data assets. | High | M | A2-4 | Each weapon defined as data (damage, radius, cooldown, VFX refs); no hard-coded stats. | To Do
A3 Gameplay parity on data | A3-2 | Tank/unit ScriptableObjects | Author Abrams, M60, T-55/62/72, Type-99 stat definitions. | High | M | A2-4 | Units defined as data (HP, armor, speed, range, archetype); designer-editable. | To Do
A3 Gameplay parity on data | A3-3 | Author original levels as Match Definitions | Recreate the four original levels as data-driven Match Definitions. | High | M | A3-1,A3-2,A2-5 | Four levels selectable and playable from data. | To Do
A3 Gameplay parity on data | A3-4 | Movement via AI Navigation | NavMeshSurface bake + agent-based tank movement. | High | M | A2-5 | Tanks path correctly on baked navmesh; no legacy NavMesh API. | To Do
A3 Gameplay parity on data | A3-5 | Port decision logic to Behavior; retire RAIN | Rebuild existing tank decisions in Unity Behavior graphs and remove RAIN DLLs. | High | L | A3-4 | RAIN.dll removed; tanks behave at parity via Behavior graphs. | To Do
A3 Gameplay parity on data | A3-6 | Control points & capture | Decoupled, event-driven control-point capture logic. | High | M | A2-5 | Capture works via events; no cross-script Find; matches original behavior. | To Do
A3 Gameplay parity on data | A3-7 | Wave spawner | Wave spawning system reading the Match Definition. | High | M | A2-5 | Waves spawn per data; pooled; counts/timing match design. | To Do
A3 Gameplay parity on data | A3-8 | Fog of war & listening posts | Reimplement FOW reveal and listening-post sightlines. | Medium | M | A2-5 | FOW reveals around units/posts; performant on device. | To Do
A3 Gameplay parity on data | A3-9 | Targeting / line-of-sight | Replace TankSight: LOS-based target acquisition. | High | M | A3-4 | Units acquire/hold targets by LOS at parity; no uncached lookups in hot path. | To Do
A3 Gameplay parity on data | A3-10 | Combat resolution | Damage, armor, napalm burn-over-time, mine stop/damage, slow-mo concentrated strike. | High | L | A3-1 | Combat math matches original; covered by unit tests. | To Do
A3 Gameplay parity on data | A3-11 | HUD & menus on events | Rebuild HUD and menus driven by state events (no GameObject.Find wiring). | High | M | A2-2 | UI updates from events; menu flow works; no Find-based wiring. | To Do
A3 Gameplay parity on data | A3-12 | Parity playtest | Full playthrough of all four levels vs the 2015 beta. | High | M | A3-3,A3-5,A3-6,A3-7,A3-8,A3-9,A3-10,A3-11 | All four levels play at parity on device; sign-off recorded. | To Do
A4 Pipelines & persistence | A4-1 | URP art-import pipeline | Import preset: scale, LODs, colliders, ASTC compression; validate with a placeholder model. | High | M | A1-1 | Placeholder model imports to spec; draw-call/memory sane; preset documented. | To Do
A4 Pipelines & persistence | A4-2 | Audio import pipeline | Compression settings; streaming for music, decompress-on-load for short SFX. | Medium | S | A1-1 | Placeholder audio imports per policy; mobile memory acceptable. | To Do
A4 Pipelines & persistence | A4-3 | Addressable groups & size budget | Organize content into Addressable groups; set an initial build-size budget. | Medium | M | A2-8 | Content grouped; build size measured against budget in CI. | To Do
A4 Pipelines & persistence | A4-4 | Save service + Cloud Save | Versioned local save + UGS Cloud Save sync. | High | M | A2-1 | Progress/settings persist across restart and sync across devices; migration-safe. | To Do
A4 Pipelines & persistence | A4-5 | Analytics wiring | Instrument session, match start/win/lose, weapon use events. | Medium | S | A2-2 | Events appear in the analytics dashboard with correct params. | To Do
A4 Pipelines & persistence | A4-6 | Remote Config integration | Expose tuning values (ammo, damage, wave size) via Remote Config. | Medium | M | A2-4 | Values fetched at boot and override defaults; safe fallback when offline. | To Do
A4 Pipelines & persistence | A4-7 | Stub mode & meta interfaces | Interfaces/stubs for the Stage B mode framework and meta-progression. | Medium | M | A2-5,A4-4 | Interfaces exist and compile; a stub mode runs; documented for Stage B. | To Do
A5 Backend, optimization & hardening | A5-1 | UGS Authentication | Anonymous-first auth, upgradeable to platform accounts. | High | S | A4-4 | Anonymous sign-in works; identity persists; upgrade path documented. | To Do
A5 Backend, optimization & hardening | A5-2 | UGS Economy skeleton | Placeholder currency and catalog to validate the economy plumbing. | Medium | M | A4-6 | Currency balance reads/writes; catalog resolves; no client-trusted balances. | To Do
A5 Backend, optimization & hardening | A5-3 | Secrets & environments | Secret management + dev/staging/prod environment configs. | High | S | A1-4 | No secrets in source; environment switch works; prod locked down. | To Do
A5 Backend, optimization & hardening | A5-4 | Device profiling pass | Profiler + Memory Profiler on target hardware; fix allocations/hotspots. | High | M | A3-12 | No steady-state per-frame allocations in combat; hotspots addressed. | To Do
A5 Backend, optimization & hardening | A5-5 | Pooling coverage audit | Ensure zero Instantiate/Destroy in combat hot paths. | High | S | A3-10 | Combat spawns/returns via pools only; verified by profiler. | To Do
A5 Backend, optimization & hardening | A5-6 | Cache component lookups | Cache GetComponent references; remove Update-loop lookups. | Medium | S | A3-12 | No per-frame GetComponent in hot paths; references cached on Awake. | To Do
A5 Backend, optimization & hardening | A5-7 | Budgets enforced in CI | Set + enforce frame time, draw calls, memory, build size, cold start. | High | M | A5-4 | CI fails when a budget is exceeded; budgets documented. | To Do
A5 Backend, optimization & hardening | A5-8 | Automated tests (combat/progression) | Edit/play-mode tests for combat math and progression. | High | M | A3-10 | Tests cover core math + progression; run green in CI. | To Do
A5 Backend, optimization & hardening | A5-9 | CI smoke tests + crash reporting | Per-scene smoke test in CI; enable Cloud Diagnostics. | Medium | S | A1-5 | Each scene loads in CI; crashes reported with symbols. | To Do
A5 Backend, optimization & hardening | A5-10 | EXIT GATE review | Verify the expansion-ready foundation checklist; go/no-go for Stage B spend. | Critical | S | A4-1,A4-4,A4-5,A4-6,A4-7,A5-4,A5-7,A5-8 | All gate criteria met and signed off; Stage B authorized. | To Do